## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Start of the week | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2022-01-02 | 2022-01-09 | 2022-01-16 | 2022-01-23 | 2022-01-30 | 2022-02-06 | 2022-02-13 | 2022-02-20 | 2022-02-27 | 2022-03-06 | 2022-03-13 | 2022-03-20 | 2022-03-27 | 2022-04-03 | 2022-04-10 | 2022-04-17 | 2022-04-24 | 2022-05-01 | 2022-05-08 | 2022-05-15
Sensing and input working package | 2021-11-21: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt project plan Members tasks asignation; 2021-11-28: Didn't have the car yet; 2021-12-12: Camera handling, preprocessing, noise cancelling, ROIs definition; 2022-01-16: Define other necessary sensors, define use-case, integration (IMU, distance), preprocessing, noise cancelling.; 2022-05-15: BFMC
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
[17 empty] | Induce noise on all sensors and systems |  |  |  |  | Other functionalities and optimizations
Perception and scene understanding working package | 2021-12-12: Lane detection; 2022-01-16: Traffic sign detection; 2022-02-13: Traffic light detection
[6 empty] | Intersection detection | [5 empty] | Position fusion |  |  |  |  | Traffic lights detection & classification
[14 empty] | Define objects properties file |  |  | Object detection & classification
Environmental server interaction
Other functionalities and optimizations
Behaviour and motion plan working package | 2021-12-12: Define project architecture and communication between packages; 2022-01-02: Define path planning and validation; 2022-02-20: Define robustness and safety measures
Define decision making --> priorities of actions and state flow
[17 empty] | Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states) |  |  |  |  | Other functionalities and optimizations
Vehicle control working packages | 2021-12-12: Lane following and speed control; 2022-01-16: Intersection navigation; 2022-02-13: Simpla action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2022-03-13: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Other functionalities and optimizations
Final result & Demo | 2021-11-21: Team can control the phisical car remotely and the virtual car on the simulator.; 2021-12-12: Robot can keep a lane, can make a curve; 2022-01-16: Robot can navigate in intersection; 2022-02-13: Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2022-03-13: While detecting and calculating it's position, the robot can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  |  |  | Team defines and creates it's own physical testing environment |  |  |  | Team defines a way of parallel developing and testing
Team installs the virtual testing environment
Other functionalities and optimizations
Deadlines | 2021-12-12: 2021-12-22; 2022-01-16: 2022-01-16; 2022-02-06: 2022-02-06; 2022-03-06: 2022-03-09; 2022-04-10: 2022-04-13; 2022-05-15: 2022-05-21
Checkpoint | 2021-12-12: 1st report; 2021-12-19: Christmas brake; 2022-01-16: Team evaluation; 2022-02-06: 2rd report; 2022-03-06: Mid-term quality gate; 2022-04-10: 4th report; 2022-05-15: Finals